## Sheet1
Defect id | test case id | Defect summary | Reproduce step | test data | Defect type | Defect severity | defect priority | expected result | actual result | Tester name | Attachements | Status
1 | 2 | check the login button | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames : standard user Password : secret_sauce | Functionality,Security | High | high | when we enter the username and password its done login properly. But does not show which user is log in. | does not show which user is log in | Parthiv Bhavsar | https://drive.google.com/file/d/1E0GK_xITvDY3mpwTXvUiKGUJwV_ds-9o/view?usp=sharing | open
2 | 3 | check the login button/with null value | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames : Password : | Functionality,Security | high | high | when we don't put value in user id and password its show only user name is require. But it's not show password is required | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1BBmo8NgfILPbcjXAJJEJ4B3IxZrPsWjG/view?usp=drive_link | open
3 | 4 | check the login button/with only user value | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames :standard_user Password : | Functionality,Security | high | high | when we put only user name and don't enter the password its show password is require but is does not show user name is valid its show in red | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1PeQNyEuMrbWDNxz3mNmpgFw1d_PpBqy8/view?usp=drive_link | open
4 | 5 | check the login button/with only password value | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames : Password :secret_sauce | Functionality,Security | high | high | when we put only password value its show user name is require that's fine but it show password in red but entered password is true. | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1oOrvDPvyrCKQqKUQ3DonXx4x7gc6rypo/view?usp=drive_link | open
5 | 6 | check the login button/with only user value with special character. | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames :!@#$% Password : | Functionality,Security | High | high | when we put specail character in user name,its show password is required in red but its also define user name in red | its not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1K6EhgjHOfCJ6OoT3Ve-pYPWEVPtAm5gX/view?usp=drive_link | open
6 | 7 | check the login button/with only password value with specal character. | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames : Password :!@#$% | Functionality,Security | High | high | when we put specail character in password name,its show user name is required in red but its also define password in red | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1MPNTuqV1ILYAfFvBhes0ZwotpaW6Jt_O/view?usp=drive_link | open
7 | 8 | check the login button/with only user value with digit number | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames :12345 Password : | Functionality,Security | High | high | when we put number in user id click the login button its show password is required its ok but its show password in red it's not proper | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1dmZNXv_GRSKSilCwrHvqFTDbAtm-p8Cx/view?usp=drive_link | open
8 | 9 | check the login button/with only password with digits number | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames : Password :12345 | Functionality,Security | High | high | when we put number in password and click the login button its show user name is required its ok but its show password in red | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1YPWytOJp-e7ISRbOdZVG17paMkScgtdJ/view?usp=drive_link | open
9 | 10 | check the login button/with only user value with digits white space | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames :poi iop Password : | Functionality,Security | High | high | when we put user is with white space its show password is require but username in red and does not show not use white space in user name | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1QEv0fBcFz3igFXRGSxurzIbJvF88yiji/view?usp=drive_link | open
10 | 11 | check the login button/with only password value with digit white space | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames : Password :poi iop | Functionality,Security | High | high | when we put password value with white space its does not show password does not take white space and it's also show password in red | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1ZcG3seOCYb0rzq-qzO1f8wKwbBIVzAQX/view?usp=sharing | open
11 | 12 | check the login button/with only user value with uppercase. | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames :WERT Password : | Functionality,Security | High | high | when we put user value in uppercase its and hit the login button its show password is required, but it's also show user id in red. | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1Ybh7iVpZHKFAoeKVkpipO7ojCqpRhewR/view?usp=sharing | open
12 | 13 | check the login button/with only password value with uppercase. | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames Password :WERT | Functionality,Security | High | high | when we put password value in password with uppercase its show password in red . | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/10FGRumhTYYR0BNvUPtK97TgLG0WYesCI/view?usp=sharing | open
13 | 14 | check the login button/with only user id value with length. | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames:gqhvvclqicwbqolicwxwcwccwcwccwccwcwdc Password : | Functionality,Security | High | high | when we put long user name and click the login button its show password is required that's fine but user id in red and does not show length limit | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1LWZmaWl9bHLsk0INmActkSxjbaFRzuKF/view?usp=sharing | open
14 | 15 | check the login button/with only password value with length. | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames: Password: gqhvvclqicwbqolicwxwcwccwcwccwccwcwdc | Functionality,Security | High | high | when we put long password and click on the login button its show user name is required. Show password in red, its does not show the limit of password length | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1Hu6EVt_kqH4U_WZqF4coBrZDdjyYy5Gf/view?usp=sharing | open
15 | 16 | check the login button/with use rid &password with wrong value. | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button | usernames:cnowo_kdcpinc Password: sccscswcc | Functionality,Security | High | high | when we enter wrong user id &password its show wrong user id &password. | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1X4BfbASf2mjZ54Nz8qcSDFYdTzh3UXwm/view?usp=drive_link | open
17 | 19 | check all item in menu | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button 4)click the menu icon | NA | functionality | high | low | when we click the all items in menu it should be open . | but all items not open while clicking | Parthiv Bhavsar | https://drive.google.com/file/d/1yrLFuoHwWrxNNeNr6avEBvdbA1iNGKJ_/view?usp=sharing | open
18 | 20 | check about in menu | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button 4)click the menu icon | NA | functionality | low | high | while clicking about it should be open website information but is redirect to the another website | its redirect to the another website | Parthiv Bhavsar | https://drive.google.com/file/d/1g5uHZFSpfOihNMXc9tsLGYIz5nxCwc5P/view?usp=drive_link | open
19 | 21 | check the reset app state in menu | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button 4)click the menu icon | NA | functionality | high | low | while clicking app reset state it should be reset the website or refresh the site but it's don't. | while clicking on the its do nothing | Parthiv Bhavsar | https://drive.google.com/file/d/1Rf67721dDflA5pAE5qg9BGVOAlyV8Fak/view?usp=drive_link | open
20 | 30 | check the continue button | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button 4)click the close menu icon 5)click the add to cart icon 6)click the continue shopping 7)click the filtering option 8)click the image link text 9)click the image link text outer side work properly add to cart and remove button 10)click the check out and clost button work properly. 11)check the check the cancel button | first name : last name: Postel code: | functionality | low | high | while empty all field and hit continue its only show enter the first name its wrong ,it must be show all field. | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1S_dLG2dP6ADP3_oIrvbtbxng9s27X0kD/view?usp=drive_link | open
21 | 31 | check the continue button | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button 4)click the close menu icon 5)click the add to cart icon 6)click the continue shopping 7)click the filtering option 8)click the image link text 9)click the image link text outer side work properly add to cart and remove button 10)click the check out and clost button work properly. 11)check the check the cancel button | first name :Parthiv last name: Postel code: | functionality | low | high | while enter only one name and hit continue its only show enter the last name does not show enter the postal code | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1Ef3Wo1iAPFPuWJUZWUaahGdHC7ygbVIw/view?usp=sharing | open
22 | 32 | check the continue button | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button 4)click the close menu icon 5)click the add to cart icon 6)click the continue shopping 7)click the filtering option 8)click the image link text 9)click the image link text outer side work properly add to cart and remove button 10)click the check out and clost button work properly. 11)check the check the cancel button | first name : last name: Parthiv Postel code: | functionality | low | high | while enter only last name and not enter the first name and postal code and hit continue its show only enter first name. | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1JdkB9lpnxAiroZlL0NYXVTUFgA4dMuS-/view?usp=drive_link | open
23 | 33 | check the continue button | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button 4)click the close menu icon 5)click the add to cart icon 6)click the continue shopping 7)click the filtering option 8)click the image link text 9)click the image link text outer side work properly add to cart and remove button 10)click the check out and clost button work properly. 11)check the check the cancel button | first name : last name: Postel code:23456 | functionality | low | high | while enter the only postal code and hit enter continue button its show only enter the first name . | it's not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1LcAM3O0a6pn88QB8lMoZxTKDGcA5asJ6/view?usp=sharing | open
24 | 34 | check the continue button | 1)https://www.saucedemo.com/ 2)click the enter button 3)click the log in button 4)click the close menu icon 5)click the add to cart icon 6)click the continue shopping 7)click the filtering option 8)click the image link text 9)click the image link text outer side work properly add to cart and remove button 10)click the check out and clost button work properly. 11)check the check the continue button | first name :any value last name: any value Postel code: any value | functionality | low | high | while we put three field simultaneously any value like special character,long,shot,digit,white space etc its take and does not show any error | its not display proper validation message | Parthiv Bhavsar | https://drive.google.com/file/d/1Ki_3XpbDFa4GbMp3QES4JroZPM6rlXNo/view?usp=sharing | open